## Sheet1
Trick Excel into Creating a Gantt Chart |  |  |  | 39695 | 39740
Tasks | Start Date | Duration (Days) | End Date
Land Preparation | 2008-09-04 | 8 | 2008-09-12
Foundation | 2008-09-12 | 4 | 2008-09-16
Framing | 2008-09-16 | 5 | 2008-09-21
Doors and Windows | 2008-09-19 | 4 | 2008-09-23
Plumbing | 2008-09-23 | 2 | 2008-09-25
Electrical | 2008-09-23 | 3 | 2008-09-26
Sheet Rock | 2008-09-26 | 12 | 2008-10-08
Finish Work | 2008-10-08 | 7 | 2008-10-15
Painting | 2008-10-10 | 9 | 2008-10-19
Steps
1 | Start by creating a stacked bar chart
2 | Remove the Data Series by right mouse clicking and choosing Select Data Source
3 | Add a new Data Source Named Starting Date, and point to the range of start dates for the values
4 | Add another new data source named Duration (Days), and point to the range of duration days for the values
5 | Add Category Axis Labels and point to the Task names in Column A
6 | Remove legend by selecting legend and pressing the Delete key
7 | Click on the beginning series and set the Fill and Borders to None
8 | Right mouse click on the task labels, choose format Axis, and check the Categories in Reverse Order box (if needed)
9 | In two blank cells, write a formula referencing the start and end dates, convert these dates to numbers with formatting
10 | Use the resulting numbers to set the scale of the Gantt Chart (perhaps use a slightly larger range of dates)
11 | Right mouse click on the date range, set the minimum and maximums to fixed using the numbers acquired in the above step
12 | Format the date range to show a short date
13 | Format the remaining data bars to display a 3-D bevel
14 | For added touch, search Google images for a nice picture of a house, save it to your hard drive.
15 | Set the background plot area to picture, and wash out the picture enough so that the chart is still readable.
16 | Add a title or text boxes as needed to complete the description of the Gantt Chart
Formulas:
End Date = [Start Date]+[Duration (Days)]
Carlton Collins Contractors Gantt Chart for Building a Home